| Step in the Process | Status | Date |
| --- | --- | --- |
| - Conduct the process mapping exercise with a multi-disciplinary team to understand current workflow and improvements that could be made to better integrate evidence-based practices (EBPs) for ASRH (may require multiple sessions) |  |  |
| - Conduct a walkthrough with a group of youth advisors using the GPCA Playbook Health Center Walkthrough Tool to get their feedback on the current clinic environment and workflow |  |  |
| - Organize a session for youth advisors to share their feedback from the walkthrough directly with the multi-disciplinary team (or facilitate alternate means of sharing thoughts via video, etc.) and develop next steps |  |  |
| - Create a draft of the improved workflow based on the improved workflow process map with EBPs created by the multi-disciplinary team and the youth advisors’ feedback from the walkthrough |  |  |
| - Identify remaining questions for the multi-disciplinary team and vet the draft workflows with them |  |  |
| - Create a draft visual depiction of the workflow and identify outstanding questions to pose to the multi-disciplinary team about the improved workflow |  |  |
| - Review the draft improved visual workflow with EBPs and youth feedback incorporated with the multi-disciplinary team and address outstanding questions to finalize the draft |  |  |
| - Vet each step within the draft improved visual workflow with youth advisors |  |  |
| - Organize another session for youth advisors to share feedback on the draft improved visual workflow directly with multi-disciplinary team (or facilitate alternate means of sharing thoughts via video, etc.) and develop next steps |  |  |
| - With the multi-disciplinary team’s input, revise draft improved visual workflow based on the feedback from the youth advisors |  |  |
| - Simulate the revised visual workflow with youth advisors via a walkthrough |  |  |
| - Finalize and implement the final improved visual workflow |  |  |

Instructions: After conducting your process mapping exercise to map out the current workflow and improvement that can be made to incorporate evidence-based practices (EBPs) for ASRH, you can follow the steps in this checklist below to embark on a process of co-design with a group of youth advisors to ensure the improvements you make to the workflow are responsive to the needs and desires of your adolescent clients.